## Sheet1
Development Module |  |  | Time (in hours) | Assumptions
HTML Layout & Theme Development
| Server Setup and third party utility application instalation & configuration (Memchaced, FFMPEG, Converter Queue, GD Library, ZLIB, GZIP Compression, Load Balancer, DB Master slave Architecture, SSL Implementation, Encrptor Engine, Varnish) |  | 90
| Layout designs and PSD Cutting for approved layout |  | 220
Responsive HTML Development
Cross Browser Testing (Chrome, FF, Safari, IE 9+)
HTML testing on mobile devices & tablets
Database Schema Design (RDBMS)
| Architecture & security design implementation |  | 80
| Table schema design & ERD |  | 36
Schema testing with dummy values
Website Modules
| Staff | Login | 480 | There is no any saperate section for suppliers & Clients. Only Site admin and staff members would manage the supplier and clients.
Administrative ability to add and modify user accounts on the system
Clients Managment
Supplier Managment
Sales & Order History
Warehouse Managment
Item Managment
RFQ's Managment
Shipping Managment
Costing Managment
Bill Creation & send to MYOB
| MYOB | MYOB integration for maintaining financial system
Admin Panel
|  | all modules should have auditing (where relevant), standard administrative information (such as create date, created by whom, update date, updated by whom etc) and notes. | 280
Staff Managment & all administrative access to manage Clients, suppliers, warehouse etc.
Testing and Bug fixing
|  | User acceptance testing | 120
Functional testing
Bug fixing
Deployment
|  | Deployment on production, staging and live server | 32
Maintain GIT or SVN repositories
Project Management & Communication
|  | Workflow design | 80
Resource management
Daily Updates
Scrum meetings
Total Estimated Hours |  |  | 1418