## Sheet1
Development Module |  | Time (in hours) | Comments
Wordpress Installation, Theme Integration & Cutomization
| Wordpress Installation | 40 | We will use ready template: http://www.templatemonster.com/demo/52089.html
Theme Customization
Cross Browser Testing (Chrome, FF, Safari, IE 9+)
Theme Integration
Website Modules
| Page layout integration and customization | 180
User Registration form
End User can add OR remove companies, events etc.
Company category & subcategory are defined and managed by admin.
Customized category menu and pages
Event Listing page customization
Event Detail page customization
Event categories and subcategories are defined and managed by admin
Buddypress integration for company wise social network & reviews
Informative Pages Managment (About Us, Contact Us, Privacy Policy)
| Price management & payment options |  | This point needs discussion & not included in this estimation.
Testing and Bug fixing
| User acceptance testing | 20
Functional testing
Deployment
| Deployment on production, staging and live server | 10
Maintain GIT or SVN repositories
Project Management & Communication
| Workflow design | 24
Resource management
Daily Updates
Scrum meetings
Total Estimated Hours |  | 274
Total Hour